## Sheet1
Raclette Team | February |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June
Tasks | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Project Kick-off
Agreement use case
AS-IS Process definition
TO-BE Process definition
Decision Modelling
Microservices & API's
Service integration
Development of Chatbot (AI)
Development of Face Recoginition
Testing
Final Presentation
Wiki Kick-off
Introduction use case
Processes Description
Decision Modelling
Chatbot
Face Recoginition
Software and tools
Conclusion